##### June 17, 2004 ## Waste and Fraud Besiege U.S. Program to Link Poor Schools to Internet By SAM DILLON ASHINGTON, June 16 - When the El Paso school system wanted to upgrade its Internet connections three years ago, it tapped into a federal program that offers assistance for such projects.. The program paid the International Business Machines Corporation $35 million to build a network powerful enough to serve a small city. But the network would be so sophisticated that the 90-school district could not run it without help. Foreseeing the problem, I.B.M. charged the district an additional $27 million, paid by the federal program, to build a lavish maintenance call-in center to keep the network running. The center operated for nine months. Then, with no more money to support it, I.B.M. dismantled it and left town. The federal effort to help poor schools connect to the Internet, the E-rate program, which collects a fee from all American phone users to distribute $2.25 billion a year to such schools and libraries, wasted enormous sums as El Paso built its extravagant network in the 2001-2 school year, according to documents and federal lawmakers. But the problems have not been there alone. In Brevard County, Fla., school officials used E-rate money to install a $1 million network server, a powerful device more suited to the needs of a multinational corporation, in a 650-pupil elementary school. And just three weeks ago in San Francisco, a subsidiary of the computer giant NEC agreed to plead guilty to two federal felony counts related to the program. Across the nation in recent months - in El Paso and in New York and Pennsylvania, in Puerto Rico and Atlanta, in Milwaukee and Chicago - investigations or audits of the program have turned up not only waste but also bid-rigging and other fraud, according to lawmakers and investigators. A report issued last week by the Federal Communications Commission, which oversees the E-rate program, said 42 criminal investigations were under way. On Thursday, Congress is to open hearings on all that has gone wrong. The hearings will be held by the House Energy and Commerce Subcommittee on Oversight and Investigations, whose chairman, Representative James C. Greenwood of Pennsylvania, says the F.C.C.'s supervision was weak. Mr. Greenwood said that since schools often must pay only 10 percent of the cost of equipment and services while E-rate picks up the rest, "contractors have mastered the art of coming into these districts, recommending gold-plated architecture, and school officials, buying at 10 cents on the dollar, take everything they recommend.'' "You couldn't invent a way to throw money down the drain that would work any better than this," he added. The Universal Service Administrative Company, a nonprofit government corporation overseen by the communications commission and known to school administrators as USAC (pronounced YOU- sack), is in charge of the E-rate program, which has many enthusiastic backers. "Every mammoth government program has problems," said Gregg Downey, editor of eSchool News, a paper that covers educational technology. "The sloth, the waste and the cases of outright fraud shouldn't be a reason to get rid of a program that's doing a lot of good. This is a program that helps schools serve students better through technology." Michael Balmoris, a spokesman for the communications commission, said that E-rate was not "waste- and fraud-free" but that abuses were not "endemic." Narda M. Jones, an acting chief in the F.C.C. division that oversees the program, said it was designed to give schools "maximum flexibility" to build technology systems that suited their needs. "But as the system has grown, we've seen that that design has given people an opportunity to push at the margins of the program," Ms. Jones said. In the last year, she said, the commission has adopted rules that "significantly tighten" the wiggle room for abuse. One such rule bars people found guilty of crimes from participation, she said. But Thomas D. Bennett, an assistant inspector general at the commission, remains concerned about oversight. He pointed to evaluations of 122 E-rate beneficiaries carried out or overseen by F.C.C. and USAC auditors in the last year or so. The auditors characterized 62 beneficiaries as "compliant" with E-rate rules, 21 as "generally compliant," and 39 - nearly a third of the total - as "not compliant," Mr. Bennett said. "That doesn't give us much comfort that beneficiaries are complying with our rules," he said. In the case of the $1 million server, installed for the Endeavour Elementary School in Cocoa, Fla., Mr. Bennett's auditors are midway through an examination of documents relating to the Brevard County school district's purchase of it. He declined to characterize the interim findings. Lee A. Berry, the Brevard district's deputy superintendent, defended the purchase. "We violated no rules," Mr. Berry said. "Was that server appropriate for that school? In our mind it was. It allowed each teacher and child to have a Web site." In El Paso, school authorities applied for a total of $10.6 million in the first three years of the E-rate program, which got under way in 1998. They used the money they received to wire classrooms and offices. Then El Paso formed a strategic alliance with I.B.M. and in December 2000 filed an application for $77 million, at least 20 times as much as in any previous year. Of that total, the E-rate agency ultimately disbursed about $62 million. The I.B.M.-El Paso plan called for creation of a fiber-optic network with videoconferencing capabilities, managed by top-of-the-line switches, routers and other hardware. The project was so sophisticated, and so much money had to be spent so fast, that the district's in-house technology staff was quickly overwhelmed. After financing was approved, I.B.M moved immediately to roll out the new network. But it took until April 18, 2002, to commence operations at the $27 million maintenance support center, Andrew Kendzie, an I.B.M. spokesman, said by e-mail in response to questions. Eleven weeks later, the budget year ended, and since I.B.M. was only renting the center to the district, its continued operation required new E-rate money. Hoping that El Paso would gain approval of a $46 million request for the new budget year - approval that never came -I.B.M. operated the maintenance center at its own expense, of $3 million, through December 2002, Mr. Kendzie said. "We informed the district that we could no longer continue to provide these services for free," he said, and in January of last year the company dismantled the maintenance center and left El Paso. Copyright 2004 The New York Times Company ¦ Home ¦ Privacy Policy ¦ Search ¦ Corrections ¦ Help ¦ Back to Top