Estimate base on Function Points

Assume:

10 inputs: 4 hard, 3, average, 3 easy

8 reports: 5 hard, 3 easy

4 queries: all easy

2 files: both average

Productivity is 6 FP/pm

Calculate Function points:

Inputs:   4 x 6 = 24 (hard)

3 x 4 = 12 (average)

3 x 3 =   9 (easy)

43

Reports: 5 x 7 = 35 (hard)

3 x 4 = 12 (easy)

47

Queries: 4 x 3 = 12 (easy)

Files:      2 x 10 = 20 (average)

Total Function Points =  122

Complexity Factors:

Backup and Recovery 				4

Data Communications				2

Distributed Processing 				0

Performance Critical				4

Existing Operating Environment			3

On-line data Entry					4

Input Transaction/ multiple Screens		5

# Master files updated on line				3

Information domain values complex		5

Internal processing complex			5

Code designed for reuse				4

Conversion/installation in design			3

Multiple installations				5

Application designed for change			5

TOTAL		          		        52

Total Function Points = 122 x (.65 + .01 x 52) =  142.7

Estimated Effort is Total Function Points / Productivity / people available

Estimated effort is 142.7 / 6 / 4  = 5.9 months